## Slide 1
Sjoerd Schenau
Introduction to the
SEEA CF research agenda

## Slide 2: Background
During the preparation of the SEEA CF, some important topics were identified that would benefit from further research and consideration.
To move the SEEA CF research agenda forward, a revised complete list of issues has been developed by the SEEA CF technical committee.
In 2016, the items on the research agenda have been prioritized and a detailed time line for 2017-2019 has been established.

## Slide 3: Process for research agenda
SEEA-CF research agenda can be updated when needed.
The proposed timeline for the topics currently identified is 3 years (2017-2019).
Lead agencies have been assigned to topics, they ensure progress in the work on the issues
For each topic a short issue paper will be written that will be discussed in the London group
After a final review by the SEEA CF Technical Committee and a formal decision by UNCEEA, the papers will be published on the SEEA website.

## Slide 4: Prioritization
 |  |  | Priority
A: Conceptual issues |  |  | 
1. | Development of classifications |  | High
2. | Development of consistent valuation techniques |  | High
3. | Definition of resource management /structure of ReMEA |  | High
4. | Depletion of natural biological resources |  | Medium
5. | Integrated framework for environmental activity accounts |  | High
6. | Losses |  | Medium
7. | Linkages and overlap between SEEA CF and SEEA EEA |  | High
8. | Fossil fuel subsidies by industry as part of climate statistics |  | High
B: Implementation issues |  |  | 
1. | Implementation issues related to classifications |  | High
2. | Approaches to the measurement of adapted goods |  | Medium
3. | Economy wide material flow accounts |  | High
4. | Input output techniques |  | Medium
5. | Global DSDs for data exchange for SDMX |  | High
6. | Recording of fishery related activities in the PSUTs and asset accounts |  | Medium
Notes: The research agenda for SEEA CF consists of two parts:
A list of conceptual issues which needs to be addressed.
A list of implementation issues which arose and needs to be addressed, and is primarily focused on methods of data collection/compilation.

## Slide 5: Time line 2017-June 2018
2017 | January | Call for papers:
 |  | 1) Classification land
 |  | 2) Integrated framework
 |  | 3) Economy wide material flow accounts
 |  | 4) Global DSDs for data exchange for SDMX
 |  | 5) Fossil fuel subsidies by industry as part of climate statistics
 |  | 6) other areas of application
 | June | UNCEEA : review progress and work plan
 | September | Issue papers ready and sent to the LG members
 | October | London group : Discussion on the research topics
 | November | Comments LG incorporated in new version issue papers
 | December | Issue papers reviewed by SEEA CF TC
2018 | January | Call for papers:
 |  | 1) Classification of residuals
 |  | 2) Development of consistent valuation techniques
 |  | 3) Definition of resource management etc.
 |  | 4) Linkages and overlap between SEEA CF and SEEA EEA
 |  | 5) Implementation issues related to the CEA classifications
 |  | 6) other areas of application
 | June | UNCEEA : review progress and work plan

## Slide 6: Work to be done this year
 |  |  | priority | When
A: Conceptual issues |  |  |  | 
1. | Development of classifications Land Environmental activities Residuals |  | High | Paper in 2017 ??? Eurostat taskforce start in 2017, paper in 2018 2018
2. | Development of consistent valuation techniques |  | High | 2018
3. | Definition of resource management /structure of ReMEA |  | High | 2018
4. | Depletion of natural biological resources |  | Medium | 
5. | Integrated framework for environmental activity accounts |  | High | First papers in 2016 Paper in 2017
6. | Losses |  | Medium | 2019
7. | Linkages and overlap between SEEA CF and SEEA EEA |  | High | Papers in 2017
8. | Fossil fuel subsidies by industry as part of climate statistics |  | High | Paper in 2017
B: Implementation issues |  |  |  | 
1. | Implementation issues related to classifications |  | High | (see A1)
2. | Approaches to the measurement of adapted goods |  | Medium | First contribution in 2017, paper in 2018
3. | Economy wide material flow accounts |  | High | Paper in 2017 ???
4. | Input output techniques |  | Medium | Paper on RME in 2017
5. | Global DSDs for data exchange for SDMX |  | High | Paper in 2017
6. | Recording of fishery related activities in the PSUTs and asset accounts |  | Medium | First discussion in 2016, paper in 2019

## Slide 7
The CF research agenda has implications for the compilation and use of ecosystem accounts:
A1. Development of classifications for
  Land use => land management practices and
  Resource management expenditures => spending on ecosystem maintenance and restoration
A2. Development of consistent valuation techniques for stocks and flows which are neither market nor near market => ecosystem values
A4. Depletion of natural biological resources => ecosystem degradation
A6 Treatment of water losses => water provisioning accounts
B3. MFA – CF PSUT reconciliation with respect to timber growth/yields, fodder provisioning etc.
Items in the CF Research agenda of relevance to ecosystem accounts